## Issues
IssuesList
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | Complete | The content from the web on the Firefox | A: Action Item | Search the data source | Huiyi Liu | 25th February,2019 | 27th February,2019 | 28th February,2019 | We get the proper resource from the website.
2 | Complete | The Spyder compiler | I: Issue | The problem of linking between database and the website | A website about the professional method | 2nd May, 2019 | 5th June, 2019 | 27th May, 2019 | We search some methods from the Internet but we haven't tried the method which is to link to the database.
3 | Complete | Database which stores the resource | I: Issue | Different meanings of repeated professional words in the source | Yiqi Huang | 23rd May, 2019 | 5th June, 2019 | 27th May, 2019 | We would like to try our best to make the different meanings reach a consensus. We also choose the best meaning as the final paraphrase for some words.
4 | Complete | Database which stores the resource | I: Issue | The lack of some professional words | Bo Feng | 18th April, 2019 | 5th June, 2019 | 27th May, 2019 | We search more than one resources and replenish the lack.
5 | Complete | Database which stores the resource | A: Action Item | Screen the uncorrelated words and the unsuitable meanings | Yifan Liu | 18th April, 2019 | 5th June, 2019 | 27th May, 2019 | The meaings form the resource we find cannot adapt to each professional word strictly.
6 | Complete | In Xshell | I: Issue | The fault of the some codes | Yuming Chen | 16th May, 2019 | 5th June, 2019 | 27th May, 2019 | Some unexpected bugs in the progress of the coding
7 | Complete | Questionnaire and the analysis of the feedback | A: Action Item | Some feedback from the interviewees in the mid-term of the project | Huiyi Liu | 10th May, 2019 | 17th May, 2019 | 20th May, 2019 | Through the feedbacks, we can modify our design in time.
Status
Part | Status | Short Introduction
Front-End | Completed | A part which users will use concretely, some methods like CSS, jQuery are incorporated into HTML.
Back-End | Completed | A part which is the most essential to the project which support the system to run, including sever and others
Database | Completed | A part which includes the data about the dictionary consist with the specific words and its definition, description, official-site.
Gantt Chart

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete